Meeting of Motcombe Neighbourhood Plan Group

1st September 2025 at 7pm, Motcombe Methodist Hall

Present: 							Apologies:

Julian Stinton (Chair)					Trish Lever

Rebecca Sutherland (Sec)

Richard Williamson						Absent:

Richard Craigmile						Jason Hood

Cat Smyth							Richard Bromley

Mike Smith							Phil Lever

Mark Smith

Will Dunlop

Jon Rose

George Butler

Outcomes and Actions

- Review of Actions from last meeting:																															Action

Budget: PC formally thanked for £800 allocation: no further funding available

until April 2026. No response from school as yet and Community Shop to review

our request at their meeting on 12th September.

Community Infrastructure Levy from Gillingham Solar Farm is a possible source

of Funding. Contact N Phillips to request for NP					JR

Use of Motcombe Village Hall for meetings at no cost: to continue discussions

with D Scully										JS

Formation of sub-group focusing on Conservation Area: ongoing			Mike S

Investigations into best practice for community engagement (update from CS):

- Success measured by effort made to engage community rather than

volume of responses

- Need to consider timing of issue of questionnaires as well as length of

time to be given to submit responses.

- Key factors: 	-identify relevant stakeholders

-consider needs of those without digital access

-which partner agencies to include: police? schools?

-referendum not a requirement but it adds weight

- Ratification of NP Constitution & Conflicts of Interest Policy:

- NP Constitution to be amended to include requirement for 75% attendance

at meetings to be quorate. JR to update and circulate draft for ratification

next meeting.										JR

- Conflicts of Interest Policy: ratified by Steering Group & to be published

on NP page of PC website.

- Dorset Council’s LP Options and consultation:

Draft a descriptive piece outlining the challenges faced in

Motcombe in adding 464 additional dwellings Dorset Council. 		JS

Before work is undertaken to produce this piece Phillip

Reece to be contacted to ask if this would be admissible and also

suggest a meeting with him to discuss.						JR

- An Integrated Plan for Motcombe & creation of sub-groups:

Although there will be considerable overlap as most NP issues are

intertwined, JS has identified the following key areas for the NP which

could be worked on by sub-groups to the Steering Group:

- Spatial Development: housing & infrastructure including paved

roads/lanes, power, lighting, drainage etc  RW to lead. 			RW

- Amenities and Services: Schools, shops, meeting halls, church,

proximity to Shaftesbury/Gillingham and their amenities/services etc

Note: Many of the concerns/comments on Motcombe FB page are

around provision of education, health etc. Need to investigate the reality

of these concerns. CS to lead. 							CS

- Environment & community: climate emergency, nature corridors,

green spaces, cycle paths, flooding, care of the elderly etc.			TBA

- Business & Enterprise: attracting businesses to Motcombe,

including issues around connectivity.						TBA

Steering Group members to reflect and feedback on the above and consider

which, if any, of these sub groups they may want to join.				ALL

- Communications and the PC:

- JS has received agreement from Liam Stacey that all communications related to

NP and Dorset LP should be made formally through the PC / informally through

WD and RC as appropriate.

- Updates on FB on NP progress: not needed yet and to inform residents on key

stages only.

- All Steering Group communications need to be via email to ensure there is an

auditable trail of information available.

- Talk to Nicky Phillips to check progress of creating NP page on PC

website.										RC

Date of next meeting: Wednesday 24th September @ 7pm (venue TBC)